MASTER TIMELINE

AI-KCP — AI-Powered Knowledge & Community Platform

Version v1.0 | Timestamp 20260920-1746 | STATUS: LOCKED | Authority: RGR-01 / AIKCP-01 signed 20-09-2026

# 1. Scheduling Basis

The approved delivery model is a 30-day engineering plan with Day 31 production/live readiness. This schedule is intentionally expressed as project days rather than calendar dates so it remains valid if the implementation start date changes.

# 2. 30-Day Schedule

| Days | Phase | Primary outputs |
| --- | --- | --- |
| 1–5 | Foundation | Repo/GitHub, project setup, configuration, Supabase integration, base security, core shell |
| 6–10 | Core Community | Auth, profiles, questions, answers, articles, comments, reactions, reports, notifications |
| 11–14 | AI Core | Provider abstraction, prompt registry, moderation, classification, summarization, AI logging/evaluation foundation |
| 15–18 | Editorial & Board | Current Affairs, source ingestion/provenance, Sanatan Board DB migration, multilingual/translation lifecycle |
| 19–21 | Community Expansion | Bookmarks/history, contributor workflow, moderation operations, notifications and common content services |
| 22–24 | Discovery | Global search, semantic/vector search, AI recommendations, related content |
| 25–26 | Media/Future-proofing | Media handling, embeds, upload limits, mobile-ready/API boundaries, future configuration |
| 27–28 | Admin/Security | Admin centre, RBAC/RLS hardening, audit, analytics, legal pages, observability |
| 29 | Integration Testing | End-to-end journeys, security validation, AI evaluation, defect correction |
| 30 | Production Readiness | CI/CD, release checks, rollback/recovery, documentation, traceability, final acceptance rehearsal |
| 31 | Go-Live / Demo | Production release and guaranteed portfolio demonstrations |

# 3. Schedule Control

Any scope change is assessed against the Day-31 demonstrations.

Security and requirements work cannot be bypassed to preserve schedule.

Daily engineering records capture actual progress versus plan.

A schedule slip is recorded as an issue/risk with impact and recovery action rather than hidden.