RAID / RISK REGISTER

AI-KCP — AI-Powered Knowledge & Community Platform

Version v1.0 | Timestamp 20260920-1746 | STATUS: LOCKED | Authority: RGR-01 / AIKCP-01 signed 20-09-2026

# 1. Purpose

Track material Risks, Assumptions, Issues and Dependencies affecting delivery. This register is a living project-control artifact; v1.0 captures the baseline known at Phase-0 closure.

# 2. Risks

| ID | Risk | Impact | Mitigation / Response | Status |
| --- | --- | --- | --- | --- |
| R-01 | Single Supabase project for v1 | Environment separation and deployment mistakes could affect production | Strict config separation, migration discipline, feature flags, RLS, server-side enforcement; no security weakening | Accepted / Controlled |
| R-02 | AI provider/model availability or limits | AI workflows may fail or degrade | Provider abstraction, bounded responses, failure handling, logging, evaluation and fallback behavior | Open |
| R-03 | AI false positives/negatives | Incorrect moderation or classification | Versioned evaluation dataset, confidence/risk, human override, audit and metrics | Controlled |
| R-04 | Email OTP delivery limits | Authentication disruption | Provider abstraction and documented provider limits; monitor delivery/failure events | Open |
| R-05 | 1 MB combined upload limit | Some media types may be operationally constrained | Configurable limit and external embeds/links where applicable | Accepted requirement |
| R-06 | 30-day scope density | Integration or polish may be compressed | WBS, daily records, Day-31 acceptance criteria and scope control | Open |
| R-07 | Security bypass via client/tool manipulation | Unauthorized actions or data access | Server-side authorization, RLS, validation and security testing | Critical control |
| R-08 | Translation inaccuracies | Meaning/legal/context risk | Preserve original, label AI translation, stale-state lifecycle, allow source view | Controlled |
| R-09 | External source rights complaint | Content removal/legal handling may be required | Attribution/provenance, admin removal workflow and audit | Controlled |
| R-10 | Documentation drift | Future AI/developer may act on stale information | Document register, versions, baseline IDs, traceability and handover | Controlled |

# 3. Assumptions

Supabase remains technically suitable for v1.

An email delivery mechanism available within the chosen operating constraints can support production OTP.

AI provider(s) expose sufficient capabilities for the mandatory AI scope or an abstraction can route supported operations.

GitHub is available for repository/CI/CD governance.

# 4. Dependencies

Supabase Auth/Postgres/Storage and RLS

AI provider(s) and model APIs

Email delivery/SMTP capability

GitHub and CI environment

Approved external Current Affairs sources

Hostinger/domain deployment for the Sanatan Board India deployment

# 5. Issues at Baseline

No unresolved requirements issue is carried forward from RGR-01. Implementation-level defects are to be recorded separately in the project issue tracker.